## Gantt Chart
PROJECT GANTT CHART - [PROJECT NAME]
Task Name | Task ID | Duration (Days) | Start Date | End Date | Apr 2024 |  |  |  | May 2024 |  |  |  | Jun 2024 |  |  |  | Jul 2024 |  |  |  | Aug 2024 |  |  |  | Sep 2024 |  |  |  | Oct 2024 |  |  |  | Nov 2024 |  |  |  | Dec 2024 |  |  |  | Jan 2025 |  |  |  | Feb 2025 |  |  |  | Mar 2025
[5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
EPIC 1: DESIGN PHASE | EPIC-001 | 28 | 04/01/2024 | 04/28/2024 | Apr 2024 W1: Completed; Apr 2024 W2: Design Team
Requirements Review & Finalization | DESIGN-001 | 7 | 04/01/2024 | 04/07/2024 | Apr 2024 W1: Completed; Apr 2024 W2: BA
System Architecture Design | DESIGN-002 | 10 | 04/08/2024 | 04/17/2024 | Apr 2024 W1: Completed; Apr 2024 W2: Tech Lead
UI/UX Design & Mockups | DESIGN-003 | 14 | 04/08/2024 | 04/21/2024 | Apr 2024 W1: Completed; Apr 2024 W2: UX Designer
Database Schema Design | DESIGN-004 | 10 | 04/15/2024 | 04/24/2024 | Apr 2024 W1: Completed; Apr 2024 W2: DB Admin
EPIC 2: DEVELOPMENT PHASE | EPIC-002 | 56 | 04/22/2024 | 06/16/2024 | Apr 2024 W1: In Progress; Apr 2024 W2: Dev Team
Feature 2.1: User Authentication & Authorization | DEV-001 | 14 | 04/22/2024 | 05/05/2024 | Apr 2024 W1: In Progress; Apr 2024 W2: Dev 1
Feature 2.2: Inventory Management Module | DEV-002 | 21 | 04/29/2024 | 05/19/2024 | Apr 2024 W1: In Progress; Apr 2024 W2: Dev 2
Feature 2.3: Reporting & Analytics | DEV-003 | 14 | 05/13/2024 | 05/26/2024 | Apr 2024 W1: Not Started; Apr 2024 W2: Dev 3
Feature 2.4: Mobile App Development | DEV-004 | 28 | 05/06/2024 | 06/02/2024 | Apr 2024 W1: Not Started; Apr 2024 W2: Dev 4
Integration & Code Review | DEV-005 | 14 | 05/27/2024 | 06/09/2024 | Apr 2024 W1: Not Started; Apr 2024 W2: Tech Lead
EPIC 3: TESTING PHASE | EPIC-003 | 28 | 06/10/2024 | 07/07/2024 | Apr 2024 W1: Not Started; Apr 2024 W2: QA Team
Unit & Integration Testing | TEST-001 | 14 | 06/10/2024 | 06/23/2024 | Apr 2024 W1: Not Started; Apr 2024 W2: QA 1
System & Performance Testing | TEST-002 | 10 | 06/24/2024 | 07/03/2024 | Apr 2024 W1: Not Started; Apr 2024 W2: QA 2
User Acceptance Testing (UAT) | TEST-003 | 10 | 06/17/2024 | 06/26/2024 | Apr 2024 W1: Not Started; Apr 2024 W2: Client
EPIC 4: DEPLOYMENT PHASE | EPIC-004 | 14 | 07/08/2024 | 07/21/2024 | Apr 2024 W1: Not Started; Apr 2024 W2: DevOps Team
Production Environment Setup | DEPLOY-001 | 3 | 07/08/2024 | 07/10/2024 | Apr 2024 W1: Not Started; Apr 2024 W2: DevOps
Data Migration | DEPLOY-002 | 5 | 07/11/2024 | 07/15/2024 | Apr 2024 W1: Not Started; Apr 2024 W2: DBA
Go-Live & Support | DEPLOY-003 | 7 | 07/15/2024 | 07/21/2024 | Apr 2024 W1: Not Started; Apr 2024 W2: Support Team
LEGEND:
Epic
Completed
In Progress
Not Started